## Product Backlog
Product Backlog
Prioritized High-Level User Story List
User Story ID | Priority | Size | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | 1 | Medium | End User | Click a link to view the top five destinations list | See the most popular locations to travel to educate myself on the best places to go.
2 | 2 | Large | End User | click profile tab and Set Profile settings to set a price limits based on user | Get the best vacation option for the users selected budget
| 3 | small | End User | customize user profile based on previous travel | the user can pick similar destinations they liked
| 4 | small | End User | List filitering options in profile | give user top 10 similar past trips
3 | 5 | Medium | End User | set a list of options for types of activities during vacation | offer selections of the activity (type) that I want to do while on vacation

## User Story Details Example
User Story Number: | 1
User Story Name: | Top Five Destination List
User Story Size: | Medium
User Story Value Statement: | As an end user, I want to click a link to view the top five destinations list, so that I can see the most popular locations to travel to educate myself on the best places to go.
Acceptance Criteria: | • Ability to click link that takes user to a page displaying top destinations • Ordered list of destinations from number-one location to the fifth most popular • Each destination on the list will have the following attributes shown: • Destination name • Destination short description (one sentence) • Destination picture • Text with embedded link to take user to top-selling travel package for that location

## User Story Details #1
User Story Number: | 1
User Story Name: | Top Destinations
User Story Size: | Medium
User Story Value Statement: | See the most popular locations to travel to educate myself on the best places to go.
Acceptance Criteria: | • populate top destinations when first logged in on home page • Display the top option first`with image • When they click on their choice of destination it will display: • Display destination information • display photos •display pricing information • provide link to book

## User Story Details #2
User Story Number: | 2
User Story Name: | Budget filter
User Story Size: | Large
User Story Value Statement: | Get the best vacation option for the users selected budget
Acceptance Criteria: | •filters options based on users budget • Brings up the top five budget friendly destination • Listed with the most affordable as the top option • Displays vacation details • Includes destination description •destination price • Destination photos • link to book

## User Story Details #3
User Story Number: | 5
User Story Name: | Vacation type selection
User Story Size: | Medium
User Story Value Statement: | offer selections of the activity (type) that I want to do while on vacation
Acceptance Criteria: | • Have a setting with a dropdown that filters vacations based on type(museums/cruises/beach/eco-travel) •provide the top five options based on criteria • List dates available • Display vacation details • Give description of vacation • view vacations pictures • destination price • link to book